## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks
0 | 2021.09.07-2021.09.14 | decided on a group project, assigned team roles, put together development configuation instructions for the team completed all iteration 0 documentation and presentation | N/A | N/A | N/A | PivotalTracker not in use yet | PivotalTracker not in use yet | PivotalTracker not in use yet | PivotalTracker not in use yet | PivotalTracker not in use yet | 43 | 34.5 | 8.5 | 9.5 | 6.5 | 1.5 | 2.33 | 3.33 | 8 | 2.83
1 | 2021.09.15-2021.09.27 | Initial code skeleton complete, team has generated a series of user stories and assigned responcible parties, git check in procedure established, completion of iteration 1 materials | code is still at a skeleton level, no severe issues present yet | communication can be a bit tricky with a single meeting time a week | try and use slack more to enhance team communication | 10 | 0 | 5 | 0 | 5 | 40.5 | 32.5 | 8 | 17 | 4 | 1 | 4 | 0 | 7.5 | 3.5
2 | 2021.09.28-2021.10.11 | Numerous core functions have been completed or are near completion: recipe searches, recipe displaying, security login/logout features, pantry item storage, recipe reccomendation, and recipe favoriting. This accounts for a number of user stories being closed. Automated unit testing and manual testing has also commensed. Additionally, a more polished UI is being developed. completion of iteration 2 materials. | the largest technical difficulty was differences in how logging in worked across the OS and development environments of various users | we lost a team member this iteration, their responcibilities were spread across the rest of the team | people came together to pick up the slack where needed | 14 | 4 | 10 | 5 | 5 | 152.5 | 143 | 9.5 | 20.5 | 6 | 9 | 79 | 15 | 21.5 | 0
|  | At this point all core user stories / pivotal tasks have been completed. Key in this iteration were the implementation of the security features, and the creation of the profile page. Tests were developed for most testable portions of the app as well. The UI was also finished. | no significant technical issues were found this iteration, however time/life did not permit us to actually deploy our app | nothing significant | none, project is finished | 18 | 0 | 10 | 10 | 0 | 68.5 | 59 | 9.5 | 10 | 1 | 2 | 34 | 6.5 | 10.5 | 0

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Jean Shalenkova | Parts 4 and 6 | Helped define requirements in iterations 0 and 1 | define our project as an MVC project | Was not involved in testing | I did the app demo and wrote notes for Kyle for the implementation portion of the presentation | Set up programming environment and skeleton of the project (on which we built up our features from, + front end for the project | Was not involved in testing | Set up programming environment and skeleton of the project (on which we built up our features from | Communicated on Slack with everyone
Yanru Zhu | Part 5 (Quality Assurance) and icon | 1. Redefine the user story I worked on (display a recipe); 2. Redefined parts of the get similar recipe user story; 3. Worked with the team to organize and drag all user stories needed into the box during team meeting. | Worked on "Overview", "Software Architecture", "UI Design" (draw a wireframe), & a small part of "Design Pattern" | Worked on all parts of the testing document | 1. Did presentation iter 1 2. Attended in final presentation | 1. Worked on the display a recipe feature; 2. Worked on part of the get similar recipe feature; 3. Refactored the front-end work in the homepage to make it responsive, and some small UI changes | 1. Developed unit test for the feature I was working on; 2. Code all selenium tests; 3. Did all manual tests that are in the report, my teammates did a lot of manual testsing when reviewing PRs and testing the main branch as well. | None | Help set up weekly team meetings; being meeting minutes taker for 3 times
Kyle Mabry | Offered suggestions for things to include | Wrote requirements for get similar recipe and get/store favorite recipes. Redefined/clarified user stories as the design of the feature became clear | Added a design pattern to the respective section | Did not assist with this document | Attended final presentation and wrote/presented the database design section of presentation as well as implementation/MVP slide | Wrote README.md draft 1 and draft 2. Implemented code for get similar recipes feature. Implemented code for get favorites, store favorites, and remove favorites features. | Implemented unit testing for favorite recipe features | Configuration of the database table for favorites recipes | Meeting minutes taker for one meeting. Supplied coding and git resources periodically to team members as needed. Communicated on slack and was available for quick Zoom meetings as needed. | Did research on implementing a Machine Learning feature whereby favorited recipes could be fed to a ML model as training data so that a suggestion could be made about a recipe that a user would enjoy.
Justin Fanning | Parts 1-3 | Helped to define tasks initially, redefined tasks I was eventually assigned as needed, worked with the team to assign task | Worked on the database portion | Was not involved with this | Created the video and PPT for iteration 0, contributed to the the final presentation PPT and took part in the presentation | Wrote code for the pantry feature: functionality and initial html page, helped with the favorite feature to eliminate some lingering bugs, fixed a login issue for users of different OSes, helped combine the pantry and favorite features into a single profile page, code for setting size limits on the pantry and the favorites, general bug fixing/trouble shooting. Minor UI refinement | develop unit tests for the pantry functions | set up the database model for the pantry, broke early code into more organized files for development | Took part in all team meetings, took minutes in one of them. Communicate with the team in slack. Helped to ensure that everything was completed and submitted on time. Helped to make sure that our project requirements were being met. Put together submissions for each iteration.

## yuting
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Kyle Mabry
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 4.5 | 3.5 | 1 | 3 - Wrote README.md file and completed lab1 5 - Gathered everyone's emails and met as a team |  |  |  | 2 |  | 1.5 |  |  | 1. Wrote the README.md 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. communication is not clear. Task assignments is not clear. | 1. Meet with team to discuss future goals | 3 - Implement solution in Python | 7
2 | 09/13-09/20 | 7 | 6 | 1 | 5 - Met as a team 3 - Completed lab2 0 - learned about Flask | 4 |  |  | 2 |  | 1 |  |  | 1. Wrote user stories in PivotalTracker 2. Learned what Flask is and how to implement | 1. no issues | 1. Meeting with team to discuss coding to be done this week | 3 - implement code in python | 8
3 | 9/20-9/27 | 8.5 | 7 | 1 | 6 - Get familiar with code Jean wrote and test run it 5 - Met as team 3 - updated README.md 0 - learned about Flask | 4 |  |  | 2 |  | 1.5 | 1 |  | 1. Updated README.md 2. Took meeting minutes | 1. Clear communication around who is working on what is a must | 1. Be available if Justin has any questions about login framework 2. Generate recommendation framework for recipes | 3 - implement recipe recommendation in Python | 8
4 | 9/27-10/4 | 22 | 20 |  | 5 - Met as team 3 - updated README.md, implemented code for similar recipes 0 - learned about Flask | 4 |  |  | 15 |  | 3 |  |  | 1. Updated README.md 2. Enabled ability for user to find similar recipes | 1. Clear communication needed around which features each team member is working on. | 1. Implement more features | 3 - Implement more features | 16
5 | 10/4-10/12 | 22 | 20 |  | 5 - Met as team 3 - implemented code for favorite recipes 0 - learned about relational databases and SQL | 4 |  |  | 15 |  | 3 |  |  | 1. Enabled ability for user to favorite recipes and remove favorite recipes | 1. PRs need to be accepted in the order that they were submitted so that code doesn't go to waste or get out of sync with main branch. | 1. Implement more features 2. Clean up code base and get ready for deployment | 3 - Implement more features | 16
6 | 10/12-10/19 | 17 | 15 |  | 5 - Met as team 3 - implemented code for favorite recipes and refactored some code so that we used fewer API calls when getting favorite recipes 4 - implemented unit testing for favorite recipes feature. 0 - learned about relational databases and SQL tables | 3 |  |  | 10 | 2 | 2 |  |  | 1. Implemented unit testing for writing favorites recipes to the database and retreiving favorites recipes | 1. PRs need to be accepted in the order that they were submitted so that code doesn't go to waste or get out of sync with main branch | 1. Study for the final, wrap up loose ends with project, deploy project on a web-server and start making $$$ for stakeholders | None, we're done with class | 0

## Yanru_Zhu
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 6 | 9 | 1.5 | 0 - read module 1 especially the QA part, a few learnings of git 1 - brainstorm requirements with the teammates 4 - work on test/quality assurance plan in SPPP 5 - communiate in the slack, ask teammates to vote, and then organise the kickoff project meeting 6 - setup git 7 - document work, for example create team folder in drive; responsible for lab1 branch merge | 1 | 0.5 |  |  | 3 | 1 | 1 | 1 | 1. Write item 5 (quality assurance) of SPPP. 2. Setup git, commit a test message. | 1. Not famliar with Flask, can not write any code using it. 2. Almost have no idea about QA theories. Have to write the SPPP based on readings of the module content and other team's work. | 1. Watch tutorials about Flask in 2 weeks. 2. Gain more knowledge about the QA process after learning next modules. | 0 - continue to learn Flask and QA. 3 - start implementing a basic code using Python and Flask. | 8
2 | 09/05-09/21 | 4.5 | 4.5 | 1 | 0 - watch the Flask youtube video shared by facilitator and API video shared by team leader; read some QA reports written by other teams in the past 4 - update SPPP's quality assurance tab based on the feedback provided by the professor 5 - set up team meeting; com in Slack for group discussions 6 - setup Python and Flask environment using docker | 1 | 1 |  |  |  | 0.5 | 1 |  | 1. Update SPPP's quality assurance tab; put in the project icon. 2. Set up protection in the main branch (branches can only be merged after at least one approval). | 1. Still not familiar with Flask. 2. Not familiar with the end-to-end automated Selenium test. | 1. Keep wathicng Flask tutorials 2. Learn Selenium test. | 0 - continue to learn Flask and QA, especially Selenium. 3 - start coding after the skeleton is set up in by the design leader. | 7
3 | 09/22-09/28 | 9 | 9 | 1.5 | 1 - Worked on one user story that is assgined to me 2 - Analyze the architecture design we used for the app and worked on that part in SDD 3 - Helped with debugging/approving the code 5 - Setup and participate the team meeting 7 - Workd on UI framework; do presentation and project demo |  | 0.5 | 2 | 0.5 |  | 0.5 |  | 4 | 1. Completed the "Overview", "Design Architecture", and "UI Design" parts in the SDD document. 2. Completed the UI framework using Lucid. | 1. Still not familair with QA testing especially Selenium. 2. Hard to gather all teammates together for meetings. | 1. Learn Selenium test. | 0 - continue to learn Flask and QA, especially Selenium. 3 - start coding the user story assigned to me. 4 - start QAing if teammates have workd on some features. | 8
4 | 09/29-10/04 | 8.5 | 8.5 | 1 | 0 - Watched selenium test tutorials & read QA documents written by other teams. 1 - Discussed with teammates to redfine some of our requirements/features are not clear enough through random checkups and slack 3 - Finsih a user story assigned to me and merged into main 4 - Write unit teset for the user story code 5 - Slack coms and setup team meeting, meeting minutes taker. | 2 | 1 |  | 3 | 1 | 1.5 |  |  | 1. Completed the "Display a Recipe" user story and merged it into main. 2. Helped QA other teammate's pull requests. | 1. Hard to reach agreement on some features with the team. Everyone may picture a feature differently. 2. Haven't been able to deploy Selenium test successfully yet. | 1. Deploy Selenium test. | 3 - help with front end coding if needed. 4 - complete a drafted version test document. | 9
5 | 10/05 -10/11 | 9 | 20.5 | 1 | 2 - Help with front-end/color-scheme design. 3 - Refactor some codes to make the user experience better, for example remove some allergy option buttons etc. Work on the similar recipe feature. 4 - Write tests and work on the testing report. 5 - Organize a random checkup meeting, attend in team meeting, meeting minutes taker. |  |  | 3 | 5 | 10 | 1.5 |  |  | 1. Refactor several things of the app: allergy button options, about page, no results page etc. 2. Write unit test and three selenium tests. 3. Conducted more than 10 manual tests. 4. Completed testing report. 5. Updated SDDD's "architecture design" section. 6. Created a dock about color and font design https://docs.google.com/presentation/d/1BGEUfYRVvPPjQu4WGoXeOQNqrTt-3488BpfwBAMDqCo/edit#slide=id.p and provide other options of the logo. 7. Help QA other teammmates' pull requests. 8. Help teammate almost finish the "get similar recipe" feature. | 1. Hard to help fix some issues due to lack of tech ability. |  | 3 - help with more front end coding if needed. 4 - continue testing and refactoring the test report. | 8
6 | 10/12 -10/29 | 9 | 11.5 | 2 | 3 - implementation - Work on the codes to make the page responsive 4 - more QA & testings 5 - organize & attend meetings and presentations 7 - update SDD |  |  |  | 4 | 4 | 1 |  | 0.5 | 1. Refactor the the front-end codes to make the homepage being responsive and especially look good on mobile 2. Add one more selenium test for the login feature 3. Add 5 more manual tests and update the testing report 4. Updated SDD's "architecture" and "design pattern" section 5. Help QA other teammate's PR requests and unit tests 6. Attend & record final presentation 7. Demo & record the selenium test | 1. Unable to set a chrome driver for selenium test in the Docker. Have to use screenshots to visually show everything.

## Aidan_Duffy
Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 6 | 5 | 1 | 0 - read module 1, read about flask and other Python frameworks 1 - brainstorm requirements with teammates, looked into vulnerabilty assessment tactics for Python web applications 5 - communiate in the slack and participated in the kickoff project meeting 6 - setup git for version control and PyCharm as my IDE 7-researched yummly, a similar product to our goal product | 3 | 1 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 1. Setup git, commit a test message 2. Helped decide project concept | 1. Not super famliar with Flask. 2. Had to leave initial meeting early, so unsure of teammate's experience with security practices and analysis. | 1. Watch tutorials about Flask. 2. Communicate with folks in Slack over the coming weeks about static analysis tools and good security practices when implementing code. | 1- learn Flask. 2. Chat with teammates on security familiarity levels 3. Help with initial design of project and initial implementation. | 8
2 | 09/14-09/20 | 7 | 5 | 2 | 0 - Read module 2 and reviewed Flask readings sent in Slack 1 - analyze requirements to be completed this coming week 5 - Communicate with team over slack and zoom 6 - Reviewed templates for frontend 7- sent team readings for security learning | 3 | 1 |  |  |  | 2 | 0.5 | 0.5 | 1. Lab 2 2. Update/some corrections on SPPP 3. Add security details to various team documentation | 1. Still familiarizing myself with Flask and front end development | Continue learning | 1 - Help Jean on implementation front 2 - Ensure secure development practices are used | 8
3 | 09/22-09/28 | 8 | 6 | 2 | 0 - Researched authentication APIs, such as Auth0 1 - Worked on the user stories assgined to me (changed from personal pantry to account creation) 2 - Analyze the architecture design we used for the app and worked on that part in SDD 5 - Discussed implementation strategy and security strategy with Justin Fanning, listened to team meeting recording 7 - Distributed learning materials for security topics | 3 | 1 | 1 |  |  | 2 |  | 1 | 1. Completed the "Security Design" part in the SDD document. 2. Edited user stories on pivotaltracker | 1. Missed this week's team meeting 2. Need to implement account creation | 1. Ensure I can attend this week's meeting(s) 2. Work with Jean and Justin to implement accounts and personal pantry | 0 - continue to learn Flask 3 - start coding the user story assigned to me. 4 - start testing my code 5 - Communicate security issues with teammates | 8
4 | 09/29-10/04 | 10 | 9 | 1 | 0 - Researched Python and Flask specific use cases for the Auth0 authentication API, and gave the team the important documentation. 1 - Discussed with teammates to redfine some of our requirements/features a meeting w/ Justin and on slack 3 - Began working on my user story of account creation and login features. Resolved some security issues in the library. 4 - Write unit teset for the user story code 5 - Slack coms and meeting with Justin re: our stories and strategies. Due to scheduling issues, wrote up a document regarding my questions and concerns for this week's meeting | 2 | 2 |  | 3 | 0.5 | 2 |  |  | 1. Setup our initial Auth0 infrastructure, familiarized team members with the setup. 2. Helped QA other teammate's pull requests. | 1. Hard to reach agreement on some features with the team. Everyone may picture a feature differently. 2.Ran into some issues and hiccups while implementing Auth0. Outdated documentation and setup files among them. | 1. Deploy Auth0 login. | 3 - Help implementing login button on the front end. Ensure the routing to the Auth0 login and database works properly. 7 - Complete this iteration's presentation. | 10
5 | 10/05 -10/11 | 15 | 12 | 3 | 0 - Researched Python and Flask specific use cases for the Auth0 authentication API further. 1 - Discussed with teammates to redfine some of our requirements/features a meeting w/ Justin and on slack 2 - Reworked database user information storage in our security design in order to ensure user unique info was not stored in plaintext. 3 - Finalized my user stories for user account creation, login, logout. 4 - Write unit teset for the user story code 5 - Slack coms and meeting with Justin re: our stories and strategies. Put together iteration 2 presentation and recorded presentation. | 0.5 | 0.5 | 1 | 7 | 2 | 4 |  |  | 1. Deployed Auth0 implementation for login and signup 2. Finished Security section of SDD 3. Helped QA team PR requests. 4. Completed iteration 2 presentation. | 1. Need to setup page permissions for security purposes (i.e. someone not logged in should not be able to visit a profile page) 2. Need to hash user id in our local database | 1. Implement security changes before Wednesday EOD deadline. | 3 - implement security issue changes. 4 - continue testing and refactoring codebase. | 5
6 | 10/12-10/19 | 15 | 10 | 4 | 7 - Edited SDD and worked on project presentation 5 - Met as team for breakouts, weekly meeting, and presentation prep/recording 3 - implemented and refactored my work on logging in, worked on adding page permissions so general users cannot perform certain actions, such as seeing a profile 2 - Designed UML diagrams for certain classes for the SDD 0 - learned about databases and testing further from those on my team who focused on those areas | 2 |  | 2 | 5 |  | 4 |  | 1 | 1. Implemented page permissions through session tokens. 2. Added Security elements to our final presentation, explaining aspects to the team. | 1. Minor bugs remained. | 1. Study for the final | None, we're done with class | 0

## Justin_Fanning
Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/13 | 7 | 5 | 2 | 0 - learn about git branching 1 - Initial Project Brainstorm, high level program functions 5 - fill out assigned SPPP sections, assorted communication with team in slack 6- set up git for our project on my machine 7 - research similar products, iteration 0 presentation, post all needed file to github when complete | 0.5 | 2 |  |  |  | 2 | 0.5 | 1 | 1. Write 3 sections of SPPP 2. Set up git, fill out team intro (Lab 1) 3. Participate in Iteration 0 presentation | 1. Not exerienced with Flask 2. Not expereinced with Pivotaltracker 3. a lot to track down and organize for this week | 1. finish Flask toutorial over the next week 2. find/take Pivotaltracker toutorial over the next week | 0 - lean Flask and Pivotaltracker 3 - implement a basic hello world on Flask 5 - help organize and plot out tasks for the next week 6 - when established implement config/environment locally | 10
2 | 9/14-9/20 | 6 | 5 | 1 | 0 - begin flask tutorials 5 - compile meeting summary, team meating | 4 |  |  |  |  | 2 |  |  | 1. Learn framework to contribute to code 2. Lab 2 - learn/create pivotaltracker tasks | 1. still learning flask | 1. continue tutorials | 0 - continue to learn flask 3 - contribute to code after skeleton is complete 5 - update SPPP based on professor comments | 8
3 | 9/21-9/27 | 8 | 6.5 | 1.5 | 0 - a bit more flask, and learned/played with API calls 1 - revised portions of the SPPP 3- aided in the debug of the initial code 5 - took part in the team meeting and other group communication 7 - collect and post docs for Iteration 1 | 3 | 1 |  | 1.5 |  | 1.5 |  | 1 | 1. revised portions of the SPPP 2. Code review to help get the initial skeleton working | 1) still catching up on background learning for project (databasese next) 2) limited time to meet as a group | 1. continue learning as necessary | 0 - learn more about databases (SQLite) 3- work on the the user pantry feature 4 - test features added 5- team discussions as coding work continues | 8
4 | 9/28-10/4 | 10 | 9 | 1 | 0 - database setup with sqlalchemy and flask 1 - discussion with team about task requirements and assignments 3 - wrote an initial bit of code for the pantry feature - backend inc. database 4 - included additional methods in pantry code to facilitate testing during development 5 - weekly group meeting and additional slack communication | 3 | 1 |  | 4 | 0.5 | 1.5 |  |  | 1. wrote initial code for the back and of the pantry feature 2. looked over submitted code | 1) a bit of a mix up on the definition of tasks and who wa responcible for them 2) a team member has dropped the course | 1) team discussion resolved confusions 2) we have reassigned the lost team member's responcibilities | 1 - pick up req. leader tasks for this next iteration 3 - revise panrty backend, help develop pantry front end 4 - write pantry unit tests 7 - look over code as pull requests are generated | 10
5 | 10/5-10/11 | 19 | 18 | 1 | 1 - discussion with team about task requirements and assignments 2 - re-thought what items the database needed to hold, reorganized file organization - grouped like functions 3 - implemented the pantry system and tied it into the existing code, added search options(all or some of the ingredients), added the pantry items as a search add on, random code troubleshooting and review 4 - wrote unit tests for the pantry functions 5 - team meeting plus assorted communication with the team |  | 0.5 | 1 | 15 | 1 | 1.5 |  |  | 1. implemented the pantry feature 2. pantry related tests 3. minor search modifications 3. resolved some issues surrounding login 4. review/QA pull requests | some random issues due to instances of implementing something just learned |  | 1. resolve any lingering bugs 2. help with code refactoring 4. continue testing PRs 3. final presentation | 8
6 | 10/12-10/18 | 16.5 | 14.5 | 2 | 0 - learned a bit about html formatting 3 - code refinement and debugging 4 - added another rest to the pantry tests 5 - participated in the team meeting, presentation, and tried to ensure tasks were completed 7- pull request examination and debugging | 1 |  |  | 12 | 0.5 | 2 |  | 2 | 1. revisions to pantry code 2. debugged the favorite recipe code 3. helped establish routing for the profile page(combo of pantry and favorites) 4. Added capacity limits to pantry and favorites 5. added an additional pantry test 6. helped to QA PR requests 7. helped to make and give final presentation | nothing significant | none | none | 0

## Jean_Shalenkova
Lead Roles: Design + Implementation Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/13 | 10 | 8 | 2 | 0 - Read module 1, research libraries/packages that are necessary for immediate setup 1 - Initial Project Brainstorm, high level program functions 2 - Basic outline of how to implement beginning features, how features will communicate with each other in-app 3,4 - write basic helloWorld in flask to make sure environment is set up correctly 5 - fill out assigned SPPP sections, Communicate to team instructions to set up project environment 6- Set up project environment 7 - research similar products, lab1 | 1 | 2 | 1.5 | 0.33 | 0.33 | 2 | 0.33 | 1 | 1. Write sections 4 and 6 of SPPP 2. Lab 1 3. Research necessities for project features 4. Set up development environment 5. write instructions for team on how to set up environment | 1. Lots of organizational work to do | 1. Complete setting up project structure and dedicating files to certain features before next team meeting | Set up project structure etc, connect API, create models and templates | 2021-04-05
2 | 09/14-09/20 | 10 | 8 | 2 | 0 - Read module 2 1 - analyze requirements to be completed this coming week 2 - figure out how to implement spoonacular api 3 - implement spoonacular api 5 - Communicate with team over slack and zoom 6 - create templates for frontend | 2 | 1 | 1 | 2 |  | 2 | 2 |  | 1. Lab 2 2. Update/some corrections on SPPP 3. Begin setting up structure of endpoints in the app | 1. Time, trying to find mistakes | Take a breather and come back to fix mistakes | Fix bugs in endpoints, possibly begin implementing user accounts | 4
3 | 09/21-09/26 | 10 | 10 | 0 | 0 - Read module 3 1 - How we will integrate account creation and new features into what we have already built 2,3,4 - Creating color aesthetic for app, Created a basic search-by-ingredient + diet/intolerances web app + checking different inputs for analysis 5 - Slack communication | 2 | 2 | 1 | 3 | 1 | 2 | 0 | 0 | The runnable code | Time management | Resolves itself; time mgmt issues due to travel | Stylesheets | 2021-04-05
4 | 9/28-10/4 | 14 | 13 | 1.5 | 0 - Read module 4, Boostrap documentation, lab3 1 - See which component styles would work for our features 2 - Choose components that will be used throughout the app for cohesive design 3 - Begin implementing front end 5 - Slack communication, meeting | 3 | 1 | 2 | 5 |  | 1.5 |  |  | Front end, Progress Report | Time difference makes communication strange | I just communicate ahead of time any time sensitive things, we plan for the time difference | Continue implementing front end | 6
5 | 10/5-10/11 | 13 | 13 |  | 0 - Read module 5, 2 - Adjust components with color scheme and stylesheets 3 - Continue implementing front end 5 - Slack communication | 2 |  | 2 | 7 |  | 2 |  |  | Front end, progress report, some parts of SDD | Our account authorization wasn't working for the everyone | Fixed | Research how to and deploy project, complete front end | 6
6 | 10/12-10-19 | 9.5 | 8 | 1.5 | 0 - Read module 6, quiz 3 1 - Divide up presentation portions 3 - Complete front end 5 - Slack communication | 4 | 1 |  | 3 |  | 1.5 |  |  | Demo of final project, write notes for Kyle for the implementation portion of the presentation | None | None | None - this is the last week!

## Andrew Fish
Lead Roles: Requirements Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 5 | 4 | 1 | 0 - read module 1 and information on Flask 1 - brainstorm requirements with team 5 - communiate in the slack and participated in the kickoff project meeting | 4 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Brainstormed and decided on the project idea | Lack of experience with Flask | Continue researching, learning, and becoming familiar with Flask | Continue learning Flask and decide project design/plan | 9
2 | 09/14-09/20 | 5 | 4 | 1 | 0 - Reviewed module 2 and Flask framework 1 - Reviewed weekly requirements | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Continued project design | Lack of experience with Flask | Contiue learning | Code implementation | 8
| 09/22-09/28 | 8 | 7 | 1 | 1 - Worked on assigned user story 2 - Analyzed design we decided on for the app 3 - Continued reviewing code 5 - participated in the team meeting | 0 | 4 | 1 | 2 | 0 | 1 | 0 | 0 | User story |  |  | Continue code implementation | 8