## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks
0
1
2
3

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## yuting
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Kyle Mabry
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 4.5 | 3.5 | 1 | 3 - Wrote README.md file and completed lab1 5 - Gathered everyone's emails and met as a team |  |  |  | 2 |  | 1.5 |  |  | 1. Wrote the README.md 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. communication is not clear. Task assignments is not clear. | 1. Meet with team to discuss future goals | 3 - Implement solution in Python | 7

## Yanru_Zhu
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 6 | 9 | 1.5 | 0 - read module 1 especially the QA part, a few learnings of git 1 - brainstorm requirements with the teammates 4 - work on test/quality assurance plan in SPPP 5 - communiate in the slack, ask teammates to vote, and then organise the kickoff project meeting 6 - setup git 7 - document work, for example create team folder in drive; responsible for lab1 branch merge | 1 | 0.5 |  |  | 3 | 1 | 1 | 1 | 1. Write item 5 (quality assurance) of SPPP. 2. Setup git, commit a test message. | 1. Not famliar with Flask, can not write any code using it. 2. Almost have no idea about QA theories. Have to write the SPPP based on readings of the module content and other team's work. | 1. Watch tutorials about Flask in 2 weeks. 2. Gain more knowledge about the QA process after learning next modules. | 0 - continue to learn Flask and QA. 3 - start implementing a basic code using Python and Flask. | 8

## Aidan_Duffy
Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 6 | 5 | 1 | 0 - read module 1, read about flask and other Python frameworks 1 - brainstorm requirements with teammates, looked into vulnerabilty assessment tactics for Python web applications 5 - communiate in the slack and participated in the kickoff project meeting 6 - setup git for version control and PyCharm as my IDE 7-researched yummly, a similar product to our goal product | 3 | 1 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 1. Setup git, commit a test message 2. Helped decide project concept | 1. Not super famliar with Flask. 2. Had to leave initial meeting early, so unsure of teammate's experience with security practices and analysis. | 1. Watch tutorials about Flask. 2. Communicate with folks in Slack over the coming weeks about static analysis tools and good security practices when implementing code. | 1- learn Flask. 2. Chat with teammates on security familiarity levels 3. Help with initial design of project and initial implementation. | 8

## Andrew Fish
Lead Roles: Requirements Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 5 | 4 | 1 | 0 - read module 1 and information on Flask 1 - brainstorm requirements with team 5 - communiate in the slack and participated in the kickoff project meeting | 4 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Brainstormed and decided on the project idea | Lack of experience with Flask | Continue researching, learning, and becoming familiar with Flask | Continue learning Flask and decide project design/plan | 9

## Justin_Fanning
Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/13 | 7 | 5 | 2 | 0 - learn about git branching 1 - Initial Project Brainstorm, high level program functions 5 - fill out assigned SPPP sections, assorted communication with team in slack 6- set up git for our project on my machine 7 - research similar products, iteration 0 presentation, post all needed file to github when complete | 0.5 | 2 |  |  |  | 2 | 0.5 | 1 | 1. Write 3 sections of SPPP 2. Set up git, fill out team intro (Lab 1) 3. Participate in Iteration 0 presentation | 1. Not exerienced with Flask 2. Not expereinced with Pivotaltracker 3. a lot to track down and organize for this week | 1. finish Flask toutorial over the next week 2. find/take Pivotaltracker toutorial over the next week | 0 - lean Flask and Pivotaltracker 3 - implement a basic hello world on Flask 5 - help organize and plot out tasks for the next week 6 - when established implement config/environment locally | 10

## Jean_Shalenkova
Lead Roles: Design + Implementation Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/07-09/13 | 10 | 8 | 2 | 0 - Read module 1, research libraries/packages that are necessary for immediate setup 1 - Initial Project Brainstorm, high level program functions 2 - Basic outline of how to implement beginning features, how features will communicate with each other in-app 3,4 - write basic helloWorld in flask to make sure environment is set up correctly 5 - fill out assigned SPPP sections, Communicate to team instructions to set up project environment 6- Set up project environment 7 - research similar products, lab1 | 1 | 2 | 1.5 | 1 | 1 (within same hour as type 3) | 2 | 1 (within same hour as type 3 and 40 | 1 | 1. Write sections 4 and 6 of SPPP 2. Lab 1 3. Research necessities for project features 4. Set up development environment 5. write instructions for team on how to set up environment | 1. Lots of organizational work to do | 1. Complete setting up project structure and dedicating files to certain features before next team meeting | Set up project structure etc, connect API, create models and templates | 2021-04-05