## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members | 2021-10-19 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | One or more individuals join the team | 1 | 1 | 2 | 50 | team leader and all members
| Lack of motivation or responsibility | Decrease in productivity because of lack of individual motivation and/or a lack of individual responsibility in the project | 2 | 3 | 3 | 36 | team leader and all members
Communication | duplicate work | Lack of communication leading to members creating duplicate work | 2 | 3 | 3 | 36 | team leader and all members
| worked on wrong components | Lack of communication leading to members completing the wrong components | 2 | 3 | 3 | 36 | team leader and all members
| useless work | Lack of communication on necessary components leading to useless work being created | 2 | 3 | 3 | 36 | team leader and all members
| inconsistent work | Inconsistent quality of work | 2 | 3 | 3 | 36 | team leader and all members
Requirements | unclear requirements | Project requirements are not clearly defined | 3 | 4 | 4 | 24 | team leader and all members
| scope creep | The scope of the project was incorrectly designed | 3 | 4 | 4 | 24 | team leader and all members
| constant requirements changes | Changing requirements requiring constant replanning | 2 | 4 | 4 | 32 | team leader and all members
Management | improper task assignments | Tasks were incorrectly assigned | 4 | 3 | 3 | 18 | team leader and all members
| improper planning | Project plan was improperly designed | 4 | 4 | 4 | 16 | team leader and all members
| lack of management skills | Management is ineffective due to lack of management skills | 3 | 2 | 2 | 24 | team leader and all members
Technology competence | Not familiar with the framework used | Framework is not familiar to all individuals working on the project | 4 | 2 | 2 | 16 | team leader and all members
| Not familiar with the programming language used | Inexperience with programming languages used in the project | 3 | 2 | 2 | 24 | team leader and all members
| Not familiar with unit testing | Individuals are inexperienced with unit testing | 2 | 2 | 2 | 32 | team leader and all members
| Other technology incompetence | Other lack of necessary technology skills necessary for the project | 3 | 2 | 2 | 24 | team leader and all members
| Not familiar with Git | Lack of experience with Git | 3 | 2 | 2 | 24 | team leader and all members
Design and implementation | Improper design | Project was incorrectly designed | 3 | 5 | 5 | 15 | team leader and all members
| improper technology stack | Project was created using an improper technology stack | 2 | 3 | 3 | 36 | team leader and all members
| Messy code | Code is messy and difficult to understand and maintain | 3 | 3 | 3 | 27 | team leader and all members
Testing | Not enough testing | Lack of testing leading to additional issues | 3 | 3 | 3 | 27 | team leader and all members
Integration and deployment | Not enough time for integration and deployment | Time constraints restricted proper integration and deployment | 2 | 5 | 5 | 20 | team leader and all members
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.